## WEEK1
Sprint Burndown Chart
António Palmeirim 63667, Duarte Inácio 62397, André Santos 62331, Tiago Santos 63390, Luis Serrano 60253, Rafeal Tavares 60608
Task ID | Task Description | Initial Estimate
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Define the work plan | Initial Estimate Day 0: 0.5; Initial Estimate Day 1: 0.5
2 | Each member updates his previous week assignments according to the reviews received | Initial Estimate Day 0: 3; Initial Estimate Day 2: 1; Initial Estimate Day 3: 1; Initial Estimate Day 4: 1
3 | Review all the updated assignments | Initial Estimate Day 0: 1; Initial Estimate Day 4: 0.5; Initial Estimate Day 5: 0.5
4 | Meeting to decide the division of User Stories for each pair | Initial Estimate Day 0: 0.5; Initial Estimate Day 5: 0.5
5 | Plan US1 (with corresponding pair) | bar: Initial Estimate Day 0; Initial Estimate Day 6
6 | Plan US2 (with corresponding pair) | bar: Initial Estimate Day 0; Initial Estimate Day 7
7 | Plan US3 (with corresponding pair) | bar: Initial Estimate Day 0; Initial Estimate Day 6
8 | Plan US4 (with corresponding pair) | bar: Initial Estimate Day 0; Initial Estimate Day 6
9 |  | Initial Estimate Day 0: 0
10 |  | Initial Estimate Day 0: 0
11 |  | Initial Estimate Day 0: 0
12 |  | Initial Estimate Day 0: 0
13 |  | Initial Estimate Day 0: 0
14 |  | Initial Estimate Day 0: 0
Completed Effort |  | 0 | 0.5 | 1 | 1 | 1.5 | 1 | 3 | 1
Remaining Effort |  | 9 | 8.5 | 7.5 | 6.5 | 5 | 4 | 1 | 0
Ideal Burndown |  | 9 | 7.7143 | 6.4286 | 5.1429 | 3.8571 | 2.5714 | 1.2857 | 0