## WEEK1
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Play and study the game for the first time | Initial Estimate Day 0: 1.5; Initial Estimate Day 1: 0.5; Initial Estimate Day 2: 0.5; Initial Estimate Day 3: 0.5
2 | Reunite with group and discuss game mechanics | Initial Estimate Day 0: 0.5; Initial Estimate Day 3: 0.5
3 | Create first User Story | Initial Estimate Day 0: 0.5; Initial Estimate Day 4: 0.5
4 | Review first User Story | Initial Estimate Day 0: 0.25
5 | Create second User Story | Initial Estimate Day 0: 0.5
6 | Review second User Story | Initial Estimate Day 0: 0.25
7 | Create third and last User Story | Initial Estimate Day 0: 0.5
8 | Review third User Story | Initial Estimate Day 0: 0.25
9 | Review all User Stories and confirming our selection of US | bar: Initial Estimate Day 0
10 |  | Initial Estimate Day 0: 0
11 |  | Initial Estimate Day 0: 0
12 |  | Initial Estimate Day 0: 0
13 |  | Initial Estimate Day 0: 0
14 |  | Initial Estimate Day 0: 0
Completed Effort |  | 0 | 0.5 | 0.5 | 1 | 0.5 | 0 | 0 | 0
Remaining Effort |  | 5.25 | 4.75 | 4.25 | 3.25 | 2.75 | 2.75 | 2.75 | 2.75
Ideal Burndown |  | 5.25 | 4.5 | 3.75 | 3 | 2.25 | 1.5 | 0.75 | 0